## Step1-Overview
Here we list down the various Epics that define the product to be made. Make sure there are enough Epics to give a comprehensive idea of what is required to achieve your product.
Epic
Camera
Player
Enemy
Boss
Level Design
Collision
Drop
Game State Management
Audio
Graphic
Save/Load Game State
Loot

## Step2-Task Backlog
Instructions
Here we list down all the tasks required to achieve our goal for the project. Use the Epics listed in Step1-Overview to come up with these tasks. All Epics should have tasks listed to achieve that Epic. Rank each task with a Priority. Each "Must Have" task needs to be assgined to someone for completion. Add names in the table of Step3-Budgeting and the assignee column will have a dropdown list for you to pick from. "Week" refers to the week the task should be started and finished. Estimate the number of hours the task might require and always set which week this task is to be completed by. Everyone can only commit a certain number of hours each week. Make sure that the total time for all tasks in a week does not exceed that commitment. When a task is completed, the Hours Estimate will be interpreted as the time taken to actually finish the task. If a task does not belong to any Epic, leave that part empty for that task.
Epic | Priority | Task | Description | Hours Estimate | Week | Assignee | Type | Completed?
Player | Must Have | Player basic movement | Player character able to move in all 2D directions. | 2 | 4 | Min Khant Ko | Code | Yes
Player | Must Have | Gravity | Basic physics to affect player and enemy characters. "Force" to bring characters down to "ground" (simulate gravity). | 2 | 5 | Min Khant Ko | Code | Yes
Player | Should Have | Velocity based movement | Basic physics to affect player and enemy characters. Movement to be influenced by "force" instead of static movement. | 2 | 7 | Min Khant Ko | Code | Yes
Player | Must Have | Basic shooting | Player character shooting basic projectiles with circle hitbox. Controlled by mouse (aiming). | 3 | 4 | Min Khant Ko | Code | Yes
Player | Must Have | Ability to slow down time | Mechanic to slow down all in game movement. Applies to enemy characters and projectiles. | 3 | 5 | Min Khant Ko | Code | Yes
Player | Must Have | Health and damage system (self) | System to manage player character taking damage from enemies. All damage and health will be easy to manage integers. | 2 | 6 | Min Khant Ko | Code | Yes
Player | Must Have | Charged shot | An alternate firing mode by holding down firing button then releasing after a certain amount of time. This projectile will deal more damage (and other effects depending on enemy) | 2 | 8 | Min Khant Ko | Code | Yes
Player | Must Have | Energy system | A resource system to manage the use of player abilities. "Solar energy" will be consumed when player uses abilities such as time delay. | 3 | 7 | Min Khant Ko | Code | Yes
Player | Could Have | Ability to dash | Player character can quickly reposition left or right a short distance. Managed by energy system. | 2 | 8 | Min Khant Ko | Code | No
Player | Could Have | Ability to stick to walls | Player character can temporarily stick to a vertical wall. | 2 | 9 | Min Khant Ko | Code | No
Player | Could Have | Ability to shoot missles | Player can cast (one input) ability that releases missles from player character that fly to aimed location. Managed by energy system. | 4 | 8 | Min Khant Ko | Code | No
Player | Must Have | Energy recharge system | Player's energy recharges over time when its day time | 2 | 6 | Leonard | Code | Yes
Player | Could Have | Alternate time ability at night | At night, player will accelerate time only for themselves instead of slowing dow time. | 2 | 8 | Min Khant Ko | Code | No
Player | Must Have | Buff Lost | Player loses buff when killed | 2 | 7 | Leonard | Code | Yes
Enemy | Must Have | Patrol Logic | Non-boss enemies will move around on the stage. If the player is within a certain range the enemies will turn on aggro and attempt to move towards the player | 3 | 4 | Bryan | Code | Yes
Enemy | Must Have | Melee enemy | Enemies that will attempt to get close to the player to inflct damage | 2 | 4 | Bryan | Code | Yes
Enemy | Must Have | Ranged enemy | Enemies that will stay a certain distance and attempt to shoot the player | 2 | 5 | Bryan | Code | Yes
Enemy | Must Have | Health and damage system (enemy) | System to manage enemies taking damage from player. All damage and health will be easy to manage integers. | 2 | 7 | Bryan | Code | Yes
Boss | Must Have | 1st Boss | The 1st Boss with varying attack patterns, can ignore platforms | 4 | 7 | Bryan | Code | Yes
Boss | Must Have | Attack pattern #1(1st Boss) | In pattern #1, the boss will attempt to shoot at the player with different variations | 4 | 7 | Bryan | Code | Yes
Boss | Must Have | Attack pattern #2(1st Boss) | In pattern #2, the boss will attempt to melee the player if they are within a certain range | 4 | 7 | Bryan | Code | Yes
Boss | Could Have | 2nd Boss | A 2nd Boss with varying attack patterns, can ignore platforms and have different gimmick from 1st Boss | 4 | 8 | Bryan | Code | No
Boss | Could Have | 2nd Boss gimmick | 2nd Boss could have a gimmick that spawns platforms in the room for the players to navigate and avoid its attacks | 8 | 8 | Bryan | Code | No
Level Design | Must Have | Transition logic between levels | Game is able to unload current level, and load to new level | 2 | 4 | Jia Win | Code | Yes
Level Design | Must Have | Room system inside levels | A level consits of multiple rooms that are linked by Doors, ensure transition (eg. Camera, player) is fast and smooth | 4 | 6 | Jia Win | Code | Yes
Level Design | Must Have | Door (Exits/Entrance) system logic | Add the logic of Doors (which will link one room to the other). | 2 | 7 | Jia Win | Code | Yes
Level Design | Must Have | Door linking logic | Make the doors, upon collision with player, transition the player to the linked room (which is stated in the Door's code.) | 4 | 8 | Jia Win | Code | Yes
Level Design | Should Have | Spawn grid when entering room | Slight optimization by loading room when player enters rather than all start of loading level | 1 | 9 | Jia Win | Code | Yes
Level Design | Must Have | Restarting level logic | Restarting level should bring player to the first room of the level | 1 | 9 | Jia Win | Code | Yes
Level Design | Must Have | Design of level 1 | The overall layout of the first level | 1 | 5 | Jia Win | Level | Yes
Level Design | Must Have | Design of level 1's rooms | The layout of first level's rooms inside | 2 | 6 | Jia Win | Level | Yes
Level Design | Could Have | Design of level 2 and rooms | The layout of second level and rooms inside | 2 | 10 | Jia Win | Level | No
Level Design | Must Have | Load level from external file | Load level from external file for easier design and easier to modify | 4 | 5 | Jia Win | Code | Yes
Level Design | Must Have | Day and Night system | Create a day and night system into the game, so the player's solar energy can only recharges overtime during the day but not the night | 3 | 5 | Leonard | Code | Yes
Collision | Must Have | Game Object Function | The base structure that creates 1 game object | 1 | 3 | Gavin | Code | Yes
Collision | Must Have | Square-Square Collision | Checks the collision between 2 square hit-boxes | 4 | 3 | Gavin | Code | Yes
Collision | Must Have | Game Object Creation | Creates a game object for every entity to allow them to have collision without having to keep creating a new function | 6 | 4 | Gavin | Code | Yes
Collision | Must Have | Circle-Circle Collision | Checks the collision between 2 circle hit-boxes | 4 | 5 | Gavin | Code | Yes
Collision | Could Have | Tweening | Prevents the spasming when colliding continuously | 6 | 6 | Gavin | Code | No
Collision | Must Have | Directional Collision Check | Checks which sides the collision is colliding on | 3 | 8 | Gavin | Code | Yes
Collision | Must Have | Snapping of Objects Positions | Snaps the object to the previous position | 3 | 9 | Gavin | Code | Yes
Collision | Must Have | Button On Click Collision | Return a bool to check if the button is clicked or not by the cursor position and button position and size | 1 | 9 | Leonard | Code | Yes
Loot | Must Have | Drop spawn when enemy is killed | Have a small percentage for drops to appear after an enemy is defeated | 2 | 6 | Leonard | Code | Yes
Drop | Must Have | Drop effects - Solar regneration | Regenerate player solar energy when collected by player | 2 | 6 | Leonard | Code | Yes
Drop | Must Have | Drop effects - Health regeneration | Regenerate player health when collected by player | 2 | 7 | Leonard | Code | Yes
Loot | Must Have | Chest loots | A loot that will spawn on the room, player can interact with it and it will drop a random buff | 1 | 8 | Leonard | Code | Yes
Drop | Must Have | Buff Attack | A buff that increase player's attack | 1 | 8 | Leonard | Code | Yes
Drop | Should Have | Buff Fire Rate | A buff that makes player shoots faster | 1 | 8 | Leonard | Code | Yes
Drop | Must Have | Buff Max Solar Energy | A buff that increase player's max solar energy | 1 | 8 | Leonard | Code | Yes
Drop | Should Have | Drop and loots with velocity | Give drops and loots some y velocity so that it will fly up when appear and slowly drop down with gravity | 2 | 7 | Leonard | Code | Yes
Drop | Should Have | Randomize the drops | Randomize the types of drops spawns | 2 | 10 | Leonard | Code | Yes
a
Game State Management | Must Have | Change between game states | Changing from one level to another, main menu, options | 2 | 4 | Jia Win | Code | Yes
Game State Management | Must Have | Main Menu, options, credit states | Create the main menu and options, credit game states | 4 | 5 | Jia Win | Code | Yes
Game State Management | Must Have | Start button | Click to enter the first level of the game | 1 | 9 | Leonard | Code | Yes
Game State Management | Must Have | Resume button | Click to resume the game after pausing | 1 | 9 | Leonard | Code | Yes
Game State Management | Must Have | Exit button | Click to exit the game or go back to main menu | 1 | 9 | Leonard | Code | Yes
Game State Management | Must Have | Credit button | Click to enter the credit scene | 1 | 9 | Leonard | Code | Yes
Game State Management | Should Have | Back button | Click to exit the credit scene and back to main menu | 1 | 9 | Leonard | Code | Yes
Audio | Must Have | Function to manage audio | Create a function for other files to be able to call and use different audio easily | 4 | 8 | Bryan | Code | Yes
Graphic | Should Have | Consolidate all render in one file | Move existing rendering code to separate file (to tidy up level source file) | 2 | 11 | Jia Win | Code | Yes
Graphic | Must Have | Day and Night graphics | Manipulate the color to make the background depending on Day/Night | 3 | 5 | Leonard | Code | Yes
Graphic | Must Have | Sun and Moon rotation | Rotate the Sun and Moon accordingly to the time for Day and Night | 2 | 10 | Leonard | Code | Yes
Graphic | Could Have | Sprite Animations | When the entity moves there should be animations playing | 4 | 10 | Gavin | Code | No
Graphic | Must Have | On Hit Particle effect | Have a simple on-hit effect when there is a collision | 6 | 8 | Gavin | Code | Yes
Graphic | Could Have | Particle Effects | Playing of effects when doing actions or when collision happens | 2 | 11 | Gavin | Code | Yes
Camera | Must Have | Basic camera movement | Camera should follow player | 1 | 4 | Leonard | Code | Yes
Camera | Should Have | Camera Lerp | Camera follow player after a small delay | 2 | 8 | Leonard | Code | Yes
Save/Load Game State | Must Have | Save points | Save points in certain rooms that allow saving of current state. These include: current room ID, current buffs, current health, and unlock progress These information will be saved to a text save file. | 2 | 7 | Min Khant Ko | Code | Yes
Save/Load Game State | Should Have | Loading save | Save point status are persistent over game sessions | 2 | 9 | Min Khant Ko | Code | Yes
Save/Load Game State | Must Have | Credits file | Game credits wll be read from a text file (stored in assets). | 2 | 9 | Min Khant Ko | Code | Yes
Graphic | Should Have | Basic player sprite | Visual sprite to represent the player character normal and time stop state. | 1 | 4 | Bryan | Art | Yes
Graphic | Should Have | Basic player bullet sprite | Visual sprite to represent the player's normal and charged bullets. | 1 | 4 | Bryan | Art | Yes
Graphic | Should Have | Basic player solar energy sprite | Visual sprite to represent the player's current solar energy reserves | 1 | 4 | Bryan | Art | Yes
Graphic | Should Have | Boss sprites | Visual sprite to represent the boss enemies. | 1 | 5 | Bryan | Art | Yes
Graphic | Should Have | Boss attack sprites | Visual sprite to represent the boss's attacks. | 1 | 5 | Bryan | Art | Yes
Graphic | Should Have | Non-boss enemy sprite | Visual sprite to represent the non-boss enemies. Melee, Ranged & Elite | 1 | 5 | Bryan | Art | Yes
Graphic | Should Have | Non-boss enemy projectile sprite | Visual sprite to represent the ranged enemies attack. | 1 | 5 | Bryan | Art | Yes
Graphic | Should Have | Background (sea) | PNG to show a sea in the background | 1 | 6 | Bryan | Art | Yes
Graphic | Should Have | Background Sun and Moon Pngs | Sun and Moon Pngs to display during day/night | 1 | 6 | Bryan | Art | Yes
Graphic | Should Have | Button Pngs | Start, Exit, Resume, Back and Credits button visual | 1 | 7 | Bryan | Art | Yes
Graphic | Should Have | Game title & Team logo | Visual of game title and team logo | 1 | 7 | Bryan | Art | Yes
Graphic | Should Have | Power Up texture | Visual to represent of the buff for power up | 1 | 6 | Leonard | Art | Yes
Graphic | Should Have | Attack Up texture | Visual to represent of the buff for attack up | 1 | 6 | Leonard | Art | Yes
Graphic | Should Have | Max Solar Energy Up texture | Visual to represent of the buff for max solar energy up | 1 | 6 | Leonard | Art | Yes
Graphic | Should Have | Solar Engery Regen texture | Visual to represent of the buff for solar energy regeneration | 1 | 6 | Leonard | Art | Yes
Graphic | Should Have | Health Regen texture | Visual to represent of the buff for health regeneration | 1 | 6 | Leonard | Art | Yes
Graphic | Should Have | Grid texture | Visual to represent of the grid tiles in map | 1 | 6 | Jia Win | Art | Yes
Graphic | Should Have | Switch Room Transition | Visual to represent of the transition between rooms | 1 | 6 | Jia Win | Art | Yes
Graphic | Should Have | Death Transition | Visual to represent of the transition when player dies | 1 | 6 | Jia Win | Art | Yes
Graphic | Should Have | UI: Enemies Health Bar | UI for Enemies health status | 1 | 12 | Bryan | Code | Yes
Graphic | Should Have | UI: Player Health Bar | UI for Player health status | 1 | 12 | Leonard | Code | Yes
Graphic | Should Have | UI: Player Solar Energy Bar | UI for Player solar energy status | 1 | 12 | Leonard | Code | Yes
Graphic | Should Have | UI: Player Power Up Buff | UI for Player power up buff status | 1 | 12 | Jia Win | Code | Yes
Graphic | Should Have | UI: Player Attack Up Buff | UI for Player attack up buff status | 1 | 12 | Jia Win | Code | Yes
Graphic | Must Have | UI: Switch Room Transition | Create a transition screen object, that is able to calculate how the transition screen image should move across the screen | 1 | 9 | Jia Win | Code | Yes
Player | Must Have | Weekly progress meeting | Weekly Discord meeting with team to check and discuss game progress | 2.5 | ALL | Min Khant Ko | Admin | Yes
Enemy | Must Have | Weekly progress meeting | Weekly Discord meeting with team to check and discuss game progress | 2.5 | ALL | Bryan | Admin | Yes
Level Design | Must Have | Weekly progress meeting | Weekly Discord meeting with team to check and discuss game progress | 2.5 | ALL | Jia Win | Admin | Yes
Camera | Must Have | Weekly progress meeting | Weekly Discord meeting with team to check and discuss game progress | 2.5 | ALL | Leonard | Admin | Yes
Collision | Must Have | Weekly progress meeting | Weekly Discord meeting with team to check and discuss game progress | 2.5 | ALL | Gavin | Admin | Yes

## TaskTypes
Task Types | Description & Requirements | Requirements
Level | For tasks related to creating levels for the project. Ideally done without hardcoding all objects in the level within code. | @Must have a beginning and an end @Meaningful choices for the player to make @Clear objective
Art | For tasks related to creating visual art assets for the project. This includes fonts. Fonts : There are some license free fonts allowed for use. Refer to forum post. This should be kept to a minimum for RTIS and IMGD students. | @Refer to the EULA that you signed at the start of the semester @Do not use existing art assets even if they are "license free" @Tools used in the generation of art assets must be license and cost free
Audio | For tasks related to finding, creating and/or getting audio assets into the project. There are audio assets provided by the school via MetaDigger. Refer to forum post. The tasks related to coding an audio system to play audio assets should be under "Code". The audio system is a coded feature. | @Refer to the EULA that you signed at the start of the semester @Usage of existing audio assets allowed only for those found in the school's MetaDigger @Do not use external existing audio assets even if they are "license free", provided for or generated by tools @Recording your own audio, editting it with a free tool and using that asset is allowed
Code | For tasks related to feature implementation and code integration. Hardcoding levels and content for the game does not fall under this category. That would be under the task type of "Level" | @Feature functions as described and intended @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Bug Fix | For tasks related to fixing bugs that have been detected. Debugging is expected to be done during coding and development, but not all bugs would get detected during that phase. | @Symptoms identified with bugs gone @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Admin | For administrative tasks like: @Team Meetings @Presentation materials @Production documents @Marketing materials

## Step3-Budgeting
Instructions
Here all members of the team declare their commitments to the project and check if the delegated workload is within what has been committed. At least 50% of the Planned Load needs to be Code tasks. If the given excel sheet formula does not auto-fill the hours from the Backlog correctly, students are to fill it in manually.
"Weekly Commitment" | Each student needs to declare the number of hours per week that they will work on the project. Every student has their own degree of ability to cope with this class and the other classes. An honest and realistic answer to this needs to be set, to better control the scope of the project and by extension, the scope of work needed to be done per individual.
"Total Commitment" | The product of Weekly Commitment and the number of weeks committed to working on this project. This will represent the total amount of work that can be done by the individual.
"Planned Load" | Total workload assigned to this individual. Only counting tasks that are Must Have. These should not exceed the total number hours stated in Total Commitment. There is an excel formula in that slot. Regardless if the formula works, the number in the cell must be reported correctly.
"Code Load" | Code Load should be more than or equal to half of the Planned Load. This is a class for Computer Science students, everyone needs to do that minimal amount of Code.
Student Name | Student DigiPen e-mail | Weekly Commitment | Total Commitment | Planned Load (Must haves) | Planned Code Load (Must haves) | Completed Load | Completed Code Load
Min Khant Ko | ko.m@digipen.edu | 6 | 30 | 23.5 | 21 | 27.5 | 25
Bryan | c.wenshingbryan@digipen.edu | 6 | 30 | 27.5 | 25 | 39.5 | 26
Leonard | k.chng@digipen.edu | 6 | 30 | 29.5 | 27 | 44.5 | 37
Gavin | ang.g@digipen.edu | 6 | 30 | 29.5 | 27 | 31.5 | 29
Jia Win | jiawin.lau@digipen.edu | 6 | 30 | 29.5 | 24 | 37.5 | 29
| Team Totals | 30 | 150 | 139.5 | 124 | 180.5 | 146

## Priorities
Priorities | Brief | Completion
Must Have | Critical, cannot do without | Yes
Should Have | Important to the project but not vital | No
Could Have | Nice to have
Won't Have | Would not contribute to your project, can do without

## Plan Grading
Grading
Teams start with an "A" grade. Accumulated penalties will be applied to lower the grade. Teams do not need to fill this page. This page is only relevant for the very first plan submission.
Penalties | Penalty Range | Penalty Given | Feedback
Step 2 "Week" not filled with the relevant week numbers. | -1 per offending task
Assigned tasks leads to member/s exceeding their time budget. Example. Assignee commits 10 hours a week for 6 weeks. 61 hours of work were assigned. Penalty given. | -2 per offending member
Tasks are too vague. Tasks title and/or description does not sufficiently inform the assignee the scope of work required and/or begin work. | -1 per 10% of tasks
Tasks too large. Requires more than a week of the assignee's commitment. Break it down into smaller tasks. Should a task require more than a week of work, a team can be set back significantly if that task is not completed by the allocated date. Penalty is high to discourage this. | -1 per offending task
Missing data on any of the Step pages. | -1 per missing data field. A data field here is defined as a single excel cell.
Workload not well distributed. Difference between workloads between two or more members is greater than 20% of the workload done by the member with a smaller workload. | -1 to -4
Priorities and/or sequences of tasks work against the completion of the project. Includes but not limited to: - "Must Have" features left to the end of the production pipeline - Key features not labelled as "Must Have" - Tasks with pre-requisites are planned to be completed without the pre-requisites completed. | -1 to -4
| Total Penalty | 0
Final Grade